## 6-12 Mos out
Picture
Done | Responsible | Six to Twelve months out:
ü
Determine event date (s)
Identify planning committee or key players
Establish planning meeting timelines
Determine goals, objectives, program outline
Submit and confirm venue reservations
Submit and confirm lodging reservations
Identify constituencies for guest lists
Confirm date with VIP's
Identify emcee, Keynote, etc
Prepare Budget estimate
Discuss Invitation list and yield
Confirm invitation lists for events and meals
Develop event database for mailing invitations and tracking RSVPS
Outline program
Brainstorm possible gift ideas
Contact designer for invitations and program designs; determine costs
Identify specific speakers and program needs; begin discussing AV needs
Get sign offs on event program ideas

## 3-6 Mos out
Done | Responsible | Three to Six months out:
ü |  | Initiate "Save the Date" mailing (if needed)
Gather speaker biographies
Obtain invitation approval
Discuss press coverage/PR (if needed)
Identify and reserve caterer and florist
Reserve Photographer
Reserve entertainment

## 3 Mos out
Done | Responsible | 3 months out
ü |  | Order gifts
Check and order necessary supplies (ie., name badge holders, pens, stamps, envelopes, notebooks, etc.)
Finalize guest list (s)
Send invitation to printer
Receive invitation from printer
Confirm speakers and speaking order, confirm topic, length, and AV
Contact florist to discuss design
Contact Caterer to discuss menu and event
Reserve Security (if needed)

## 2 Mos out
Done | Responsible | Two months Out:
ü
Mail invitaions 8-10 weeks out
Finalize Program
Facility walk through with C&E and CTS
Determine signage

## Month of
Done | Responsible | Month of
ü
RSVP's due 2 weeks prior
Send rooming list to hotels
Make any publicity/press arrangements
Have signage created
|  | Send setup requests to C&E, CTS and others as needed | (room configuration, rectangular, rounds, classroom style)
Send agenda, dress code, direction, map, parking to guests/speakers
Follow up on pending guests
Run first batch of name badges
Wrap Gifts
Develop scripts for Key speakers
Draft and distribute cue sheets
Plan seating arrangements for dinner
List photo opportunities for photographer and reconfirm
Set task assignments/determine responsibilities
Confrim Catering (72 hrs out)
Confirm AV, florist, Media
Confirm Safety and Security
Register alcohol "social event" with S&S
Confirm transportation for VIPs/key note
Distribute guest list to appropriate parties
Run final name badges and place cards
Set-up on-site run through
Set up sound checks
Confirm honorarium amount (s)

## Day of
Done | Responsible | Day of
ü
Arrive at location
Bring registration materials: guest lists, name badges, place cards, signage, gifts, etc.
Review details and walk through the event with all staff and volunteers
Point out Restrooms, elevators and accessible entrances, and emergency exits
Bring extra copies of schedules, cue sheets, instructions, etc.
Check in with caterer and provide them with any last minue changes or special meal requests
Check Weather

## Post Program
Done | Responsible | Post
ü
Distribute any necessary gifts to non-attendees
Distribute photographs to VIP's
Hold Debrief
Complete Budget
Send thank you's to vendors, caterers, AV staff and others
Update final event attendance
Close out folder